FORM A

REPUBLIC OF MAURITIUS

(Insert Public Body’s Name)

# Indicative Annual Procurement Plan

(Insert Financial Year)

| Last Updated: |  | To be updated at least every six months |  |  |  |
| --- | --- | --- | --- | --- | --- |
| S.No. | Type/Nature of Procurement | Procurement Details | Cost Estimate (Rs) | Procurement Method to be used | Expected Date of launching of Bid |
| 1 | Consultancy | Consultancy Services - National Policy Paper on family - Audit on areas of cooperation | 700,000 700,000 | RFP | July 2021 |
| 2 | Works | Supply, Installation and Commissioning Solar water heater, water tank and water pump Notre dame | 200,000(exc. Vat) | IQ | July 2021 |
| 3 | Works | Supply, Installation and Commissioning Solar water heater la cigogne | 80,000(exc. Vat) | IQ | July 2021 |
| 4 | Works | Supply, Installation and Commissioning water pump Flacq | 40,000(exc. Vat) | IQ | July 2021 |
| 5 | Goods | Mineral water0.5 lt | 175,000 | RFQ | August 2021 |
| 6 | Goods | Juice 200 ml | 275,000 | RFQ | August 2021 |
| 7 | Goods | Stationery | 350,000 | IQ | August 2021 |
| 8 | Goods | Photocopy Paper | 350,000 | RFQ | August 2021 |
| 9 | Goods | Toner | 2,000,000 | RFQ | October 2021 |
| 10 | Goods | Leaflets - Foster Care Programme (1500 in English) and (1500 in Creole). - Back-to-Home Programme (1500 English) and(1500Creole). | 25,000 25,000 | D.P(Govt. Printing)/IQ | April 2022 |
| 11 | Goods | Pamphlets - outlining the Services and Programmes of the Child Development Unit (CDU). - IEC: CSEC Pamphlets (2000 Pamphlets and 1500 Posters) - IEC: CSEC Poster, Websites, Broadcasts on TV and 03 Billboards | 16,000 40,000 60,000 | DP |  |
| 12 | Goods | Booklet: 2000 Pamphlets on ‘Alternative Ways of Disciplining the Child’ | 16,000 | DP | August 2021 |
| 13 | Goods | Drop-in-Center: Purchase of Vehicles | 1.2M | RB | February 2022 |
| 14 | Goods | Acquisition of IT Equipment - CDU | 400,000 | RB | March 2022 |
| 15 | Goods | Acquisition of Furniture - CDU |  | RFQ | March 2022 |
| 16 | Services | IEC CAMPAIGN family - Enlistment of supplier for clip - Enlistment of supplier for design and printing of booklets | 300,000 400,000 | RFQ RFQ | April 2022 |
| 17 | Goods | Interfaith forum family - Design and Printing of Information Pack | 200,000 | IQ | April 2022 |
| 18 | Goods | Publications - Publication of the National Gender Policy 2021-2030 - Publications of Pamphlets for services to be offered in the Wellness Centres for Women | 75,000 | DP | April 2022 |
| 19 | Goods Services | Gender /International Women’s Day Organisation of International Women’s Day 2022 Juice,cakes,etc. Rental of Buses | 1,000,000 900,000 | RFQ RFQ | February 2022 |
| 20 | Consultancy | An impact analysis study of the programmes implemented at the level of the Ministry of Gender Equality and Family Welfare to address gender based violence and promote family welfare | 300, 000 | Consultancy | April 2022 |
| 21 | Goods | Office Equipment SWD | 150,000 | IQ/RFQ | February 2022 |
| 22 | Goods | Office Furniture SWD | 150,000 | IQ/RFQ | March 2022 |
| 23 | Goods | Paints and Accessories SWD | 200,000 | IQ/RFQ | February 2022 |
| 24 | Goods | Plant and Equipment SWD | 75,000 | IQ | February 2022 |
| 25 | Goods | IT Equipment (Digitisation) SWD | 600,000 | RB | February 2022 |
| 26 | Services | Video clips icw Children’s Act | 3M | RB | March 2022 |
| 27 | Consultancy | Consultancy CEDAW | 600,000 | Consultancy | March 2022 |

Date: 22 March 2022

Note:	 The information given is for planning purposes and is subject to revision or cancellation.  It does not constitute a final commitment to buy the goods and services until the procurement process is initiated.